## Sheet1
Original order | Feature | Urgency 1=most | Rel | Who (& complexity) Yellow = low Orange = high | Issue | Status |  | Progress | Comment | Priority 1= High | Complexity Factor 1=Low | Track = 0 Model=1 Info=2 | Allocated = 1 Not allocated = 5 | Low no. = good
18 | All properties conditional | 1 | 2.7 | ND |  | Evaluation required |  |  | Both YANG and documentation | 1 | 2 | 1 | 1 | 2
54 | Correction to mandatory attributes | 1 | 2.7 2.1.3 | ND | #605 |  |  |  | Both 547 and remainder of min/max value in YANG | 1 | 2 | 1 | 1 | 2
15 | Config false issues and development of YANG profiling methods | 1 | 2.7 | Group (ND) | #620 | Bug fix and strategy | https://github.com/Open-Network-Models-and-Interfaces-ONMI/TAPI-Activities/blob/main/ContributionsForDiscussions/onmi2025.ND.001-YangConfigStatements.pptx |  | Change to approach (and potential compatibility issue) | 1 | 3 | 1 | 1 | 3
61 | Attribute Type for Switch Control needs to be corrected to conditional | 1 | 2.7 2.1.3 | ND | #606
62 | String restrictions in earler releases conflict with INVENTORY_ID | 1 | 2.5 2.1.3 | ND | #622
63 | Add physical route to 2.1.3 | 1 | 2.1.3 | ND | Needed |  |  | Draft YANG ready | TIP request
64 | Process for applying fixes to previous releases and anouncing fixes | 1 | 2.1.3 2.5 | ND | #618
65 | Protobuf file should be back propagated to 2.5 | 1 | 2.5 | ND | #619
66 | Link creation and modification via a service | 1 | 2.7 | ND | #624 |  |  | Sketch available
7 | IETF-TAPI model linkage (CEP/NEP to RFC8345 TP) | 2 | 2.7 | ND |  | Proposal ready | otcc2023.ND.001_BriefAnalysis-TapiIetfModelLinkage.pptx |  | Was available for 2.5 but not implemented | 1 | 1 | 1 | 1 | 1
46 | Validate that the node-device relationship provides the opportunity for n:m. | 2 | 2.7 | ND |  | Validation |  | Confirmed | Expected to be OK | 1 | 1 | 1 | 1 | 1
9 | Align PM streaming with OAM model advancements | 2 | 2.7 | ND |  | Validation ++ |  |  | May be no changes required | 1 | 2 | 1 | 1 | 2
53 | ODU UUID missing in UC2b | 2 | 2.7 | KK | #611 |  |  |  |  | 1 | 1 | 2 | 1 | 2
57 | LLDP Snooping | 2 | 2.7 | BJ | #599 |  |  |  | Relatively simple, but requires someone to lead this | 1 | 2 | 1 | 1 | 2
58 | OTN Trail Trace | 2 | 2.7 | BJ | #598 |  |  |  | Relatively simple, but requires someone to lead this | 1 | 2 | 1 | 1 | 2
30 | Where to report what (state should be separate stream/notification v delta stream/notification ) | 2 | 2.7 | Group (ND) |  | Discussion first |  |  | May be no change in 2.7. Preparing the ground for beyond 2.7. | 1 | 3 | 1 | 1 | 3
31 | Use streaming strategy for notification reporting (existing issue) | 2 | 2.7 | Group (ND) | #607 | Discussion first |  |  | Significant history and complexity | 1 | 3 | 1 | 1 | 3
60 | Compliance validation tooling | 2 | 2.7 | ND |  |  |  |  | Requires follow up wit TIP | 1 | 3 | 1 | 1 | 3
45 | Requirements and use cases wrt compliance assessment | 2 | 2.7 | Group (ND) |  | Discussion first |  |  | Expect to report on the challenges to TIP. | 1 | 2 | 2 | 1 | 4
5 | Pluggable use cases (considering IETF work) | 3 | 2.7 | ND |  | Monitoring task | https://github.com/ietf-ccamp-wg/draft-ietf-ccamp-actn-poi-pluggable-usecases-gaps |  | Work under way in IETF. May cause changes in 2.7. | 1 | 2 | 0 | 1 | 0
8 | Problem management (IETF incident work) | 3 | 2.7 | ND |  | Monitoring task | https://datatracker.ietf.org/doc/draft-ietf-nmop-terminology/ |  | Work under way in IETF. Just for info. Will be beyond 2.7. Aim is no work in TAPI. | 3 | 2 | 0 | 1 | 0
12 | Optical impairment alignment with IETF (compatibility issue needs to be handled) | 3 | 2.7 | ND |  | Monitoring task | https://github.com/italobusi/actn-wdm-pluggable-modelling |  | Work under way in IETF. May cause changes in 2.7. | 1 | 2 | 0 | 1 | 0
25 | Streaming and YANG push (considering IETF work) | 3 | 2.7 | ND |  | Monitoring task |  |  | Work under way in IETF. Just for info. No change planned currently. Also look at -lite | 3 | 2 | 0 | 1 | 0
36 | Spec model enhancements and development of spec language (with IETF) | 3 | 2.7 | ND |  | Monitoring task |  |  | Work starting in IETF. Aim for alignment beyoind 2.7. | 2 | 5 | 0 | 1 | 0
38 | IETF Equipment assessment | 3 | 2.7 | ND |  | Monitoring task | https://github.com/ietf-ivy-wg/network-inventory-yang |  | Work under way in IETF. Potential future change in TAPI. | 2 | 2 | 0 | 1 | 0
39 | IETF Topology assessment | 3 | 2.7 | ND |  | Monitoring task |  |  | Proposed refinements in IETF. For discussion on future alignment. | 2 | 2 | 0 | 1 | 0
56 | Creation of interdomain links | 3 | 2.7 | KK | #600 |  |  |  | Need clarity on what is required where. | 1 | 2 | 1 | 1 | 2
10 | Spotlight/snapshot stream | 3 | 2.7 | ND |  | Proposal ready | otcc2024.ND.002_SpotlightAndSnapshotStreams.pptx |  | Provides an opportunity to derive current data (which is deprecated). | 1 | 3 | 1 | 1 | 3
19 | Security | 3 | 2.7 | JS | [5 empty] | 1 | 3 | 1 | 1 | 3
50 | Deprecation strategy | 3 | 2.7 | Group (ND) |  | Discussion first |  |  | May need to use any refinements to the approach in 2.7. | 1 | 3 | 1 | 1 | 3
2 | Connectivity Service and path computation service advancements (multiple alternatives, deep computations, rebalancing, including preparation for specific work beyond 2.7 | 3 | 2.7 | ND |  | Rough proposal in place for discussion | otcc2020.ND.010_TAPI-ConnectivityServiceComputationService.pptx |  | This is unlikely to deliver significant feature content in 2.7 but is necessary ground work for beyond 2.7. | 1 | 4 | 1 | 1 | 4
13 | Power along a connection | 3 | 2.7 | ND |  | Requires proposal |  |  | Potential feature delivery in 2.7 | 2 | 2 | 1 | 1 | 4
16 | Remove all RPCs |  | ? | [5 empty] | Simple, but someone needs to do this | 2 | 1 | 1 | 5 | 10
32 | Manual switch operation |  | ? | [6 empty] | 2 | 1 | 1 | 5 | 10
55 | Temperature should be a PM and not attribute |  | ? |  | #601 |  |  |  | Requires discussion and potential change | 2 | 1 | 1 | 5 | 10
3 | SIP/NEP capability model |  | ? | [6 empty] | 1 | 3 | 1 | 5 | 15
14 | OAM review and refinement |  | ? | [6 empty] | 1 | 3 | 1 | 5 | 15
52 | TAPI availability mechanism… GR |  | ? | [6 empty] | 1 | 3 | 1 | 5 | 15
11 | Same value suppression stream |  | ? | [6 empty] | 2 | 2 | 1 | 5 | 20
21 | Use case numbering elsewhere |  | ? | [6 empty] | 2 | 1 | 2 | 5 | 20
22 | Multiple context |  | ? | [6 empty] | 2 | 2 | 1 | 5 | 20
23 | Multi-band management extensions |  | ? | [6 empty] | 2 | 2 | 1 | 5 | 20
27 | Lifecycle dependencies and aggregations |  | ? | [6 empty] | 2 | 2 | 1 | 5 | 20
28 | Admin state for physical |  | ? | [6 empty] | 2 | 2 | 1 | 5 | 20
47 | Modelling equipment removal when equipment is supporting services. |  | ? | [6 empty] | 2 | 2 | 1 | 5 | 20
59 | Client and server uuid in connectivity service |  | ? | [6 empty] | 2 | 2 | 1 | 5 | 20
1 | Temporal model |  | ? | [6 empty] | 2 | 3 | 1 | 5 | 30
24 | Correlation of events |  | ? | [6 empty] | 2 | 3 | 1 | 5 | 30
29 | State propagation |  | ? | [6 empty] | 2 | 3 | 1 | 5 | 30
33 | Generalized task (from OAM job) |  | ? | [6 empty] | 2 | 3 | 1 | 5 | 30
40 | Refinement of intent modelling |  | ? | [6 empty] | 2 | 3 | 1 | 5 | 30
41 | Profiles and templates review and refinement |  | ? | [6 empty] | 2 | 3 | 1 | 5 | 30
42 | Equipment intent |  | ? |  |  |  | otcc2023.ND.007_BasicPhysicalIntent.zip |  |  | 2 | 3 | 1 | 5 | 30
43 | Intent lifecycle and improvements to initialization values |  | ? | [6 empty] | 2 | 3 | 1 | 5 | 30
44 | Linking intent and actual for presentation |  | ? | [6 empty] | 2 | 3 | 1 | 5 | 30
48 | Dealing with network growth, reconfiguration and equipment type transition |  | ? | [6 empty] | 2 | 3 | 1 | 5 | 30
49 | Get Ethernet model from MEF |  | ? | [6 empty] | 2 | 3 | 1 | 5 | 30
4 | Expand on complex digital payload mappings (modular diagrams) |  | ? | [6 empty] | 2 | 2 | 2 | 5 | 40
17 | Improved documentation on POST and DELETE |  | ? | [6 empty] | 2 | 2 | 2 | 5 | 40
26 | Description in YANG/UML not good in many places |  | ? | [6 empty] | 2 | 2 | 2 | 5 | 40
37 | UNI modelling |  | ? | [6 empty] | 2 | 2 | 2 | 5 | 40
6 | More on 3R scenarios |  | ? |  | #597 |  |  |  |  | 2 | 3 | 2 | 5 | 60
20 | RIA improvements (monolith) |  | ? | [6 empty] | 2 | 4 | 2 | 5 | 80
34 | All properties conditional |  | ? | [5 empty] | Duplicate of 18 | 2 | 1 | 1 | 99 | 198
35 | Path computation/connectivity computation enhancements |  | ? | [5 empty] | Duplicate of 2 | 2 | 1 | 1 | 99 | 198
51 | Topology discovery… LLDP and TTI |  | ? | [5 empty] | Duplicate of 57/58 | 2 | 1 | 1 | 99 | 198