## Sheet1
Original order | Feature | Who (& complexity) Yellow = low Orange = high | Issue | Status | Comment | Priority 1= High | Complexity Factor 1=Low | Track = 0 Model=1 Info=2 | Allocated = 1 Not allocated = 5 | Low no. = good
5 | Pluggable use cases (considering IETF work) | ND |  | Monitoring task | Work under way in IETF. May cause changes in 2.7. | 1 | 2 | 0 | 1 | 0
8 | Problem management (IETF work) | ND |  | Monitoring task | Work under way in IETF. Just for info. Will be beyond 2.7. Aim is no work in TAPI. | 3 | 2 | 0 | 1 | 0
12 | Optical impairment alignment with IETF (compatibility issue needs to be handled) | ND |  | Monitoring task | Work under way in IETF. May cause changes in 2.7. | 1 | 2 | 0 | 1 | 0
25 | Streaming and YANG push (considering IETF work) | ND |  | Monitoring task | Work under way in IETF. Just for info. No change planned currently. Also look at -lite | 3 | 2 | 0 | 1 | 0
36 | Spec model enhancements and development of spec language (with IETF) | ND |  | Monitoring task | Work starting in IETF. Aim for alignment beyoind 2.7. | 2 | 5 | 0 | 1 | 0
38 | IETF Equipment assessment | ND |  | Monitoring task | Work under way in IETF. Potential future change in TAPI. | 2 | 2 | 0 | 1 | 0
39 | IETF Topology assessment | ND |  | Monitoring task | Proposed refinements in IETF. For discussion on future alignment. | 2 | 2 | 0 | 1 | 0
7 | IETF-TAPI model linkage (CEP/NEP to RFC8345 TP) | ND |  | Proposal ready | Was available for 2.5 but not implemented | 1 | 1 | 1 | 1 | 1
46 | Validate that the node-device relationship provides the opportunity for n:m. | ND |  | Validation | Expected to be OK | 1 | 1 | 1 | 1 | 1
9 | Align PM streaming with OAM model advancements | ND |  | Validation ++ | May be no changes required | 1 | 2 | 1 | 1 | 2
18 | All properties conditional | ND |  | Evaluation required | Both YANG and documentation | 1 | 2 | 1 | 1 | 2
53 | ODU UUID missing in UC2b | KK | #611 |  |  | 1 | 1 | 2 | 1 | 2
54 | Correction to mandatory attributes | ND | #605 | also 2.1.3 | Both 547 and remainder of min/max value in YANG | 1 | 2 | 1 | 1 | 2
56 | Creation of interdomain links | KK | #600 |  | Need clarity on what is required where. | 1 | 2 | 1 | 1 | 2
57 | LLDP Snooping | BJ | #599 |  | Relatively simple, but requires someone to lead this | 1 | 2 | 1 | 1 | 2
58 | OTN Trail Trace | BJ | #598 |  | Relatively simple, but requires someone to lead this | 1 | 2 | 1 | 1 | 2
10 | Spotlight/snapshot stream | ND |  | Proposal ready | Provides an opportunity to derive current data (which is deprecated). | 1 | 3 | 1 | 1 | 3
15 | Config false issues and development of YANG profiling methods | Group (ND) | #620 | Bug fix and strategy | Change to approach (and potential compatibility issue) | 1 | 3 | 1 | 1 | 3
19 | Security | JS |  |  |  | 1 | 3 | 1 | 1 | 3
30 | Where to report what (state should be separate stream/notification v delta stream/notification ) | Group (ND) |  | Discussion first | May be no change in 2.7. Preparing the ground for beyond 2.7. | 1 | 3 | 1 | 1 | 3
31 | Use streaming strategy for notification reporting (existing issue) | Group (ND) | #607 | Discussion first | Significant history and complexity | 1 | 3 | 1 | 1 | 3
50 | Deprecation strategy | Group (ND) |  | Discussion first | May need to use any refinements to the approach in 2.7. | 1 | 3 | 1 | 1 | 3
60 | Compliance validation tooling | ND |  |  | Requires follow up wit TIP | 1 | 3 | 1 | 1 | 3
2 | Connectivity Service and path computation service advancements (multiple alternatives, deep computations, rebalancing, including preparation for specific work beyond 2.7 | ND |  | Rough proposal in place for discussion | This is unlikely to deliver significant feature content in 2.7 but is necessary ground work for beyond 2.7. | 1 | 4 | 1 | 1 | 4
13 | Power along a connection | ND |  | Requires proposal | Potential feature delivery in 2.7 | 2 | 2 | 1 | 1 | 4
45 | Requirements and use cases wrt compliance assessment | Group (ND) |  | Discussion first | Expect to report on the challenges to TIP. | 1 | 2 | 2 | 1 | 4
16 | Remove all RPCs |  |  |  | Simple, but someone needs to do this | 2 | 1 | 1 | 5 | 10
32 | Manual switch operation |  |  |  |  | 2 | 1 | 1 | 5 | 10
55 | Temperature should be a PM and not attribute |  | #601 |  | Requires discussion and potential change | 2 | 1 | 1 | 5 | 10
3 | SIP/NEP capability model |  |  |  |  | 1 | 3 | 1 | 5 | 15
14 | OAM review and refinement |  |  |  |  | 1 | 3 | 1 | 5 | 15
52 | TAPI availability mechanism… GR |  |  |  |  | 1 | 3 | 1 | 5 | 15
11 | Same value suppression stream |  |  |  |  | 2 | 2 | 1 | 5 | 20
21 | Use case numbering elsewhere |  |  |  |  | 2 | 1 | 2 | 5 | 20
22 | Multiple context |  |  |  |  | 2 | 2 | 1 | 5 | 20
23 | Multi-band management extensions |  |  |  |  | 2 | 2 | 1 | 5 | 20
27 | Lifecycle dependencies and aggregations |  |  |  |  | 2 | 2 | 1 | 5 | 20
28 | Admin state for physical |  |  |  |  | 2 | 2 | 1 | 5 | 20
47 | Modelling equipment removal when equipment is supporting services. |  |  |  |  | 2 | 2 | 1 | 5 | 20
59 | Client and server uuid in connectivity service |  |  |  |  | 2 | 2 | 1 | 5 | 20
1 | Temporal model |  |  |  |  | 2 | 3 | 1 | 5 | 30
24 | Correlation of events |  |  |  |  | 2 | 3 | 1 | 5 | 30
29 | State propagation |  |  |  |  | 2 | 3 | 1 | 5 | 30
33 | Generalized task (from OAM job) |  |  |  |  | 2 | 3 | 1 | 5 | 30
40 | Refinement of intent modelling |  |  |  |  | 2 | 3 | 1 | 5 | 30
41 | Profiles and templates review and refinement |  |  |  |  | 2 | 3 | 1 | 5 | 30
42 | Equipment intent |  |  |  |  | 2 | 3 | 1 | 5 | 30
43 | Intent lifecycle and improvements to initialization values |  |  |  |  | 2 | 3 | 1 | 5 | 30
44 | Linking intent and actual for presentation |  |  |  |  | 2 | 3 | 1 | 5 | 30
48 | Dealing with network growth, reconfiguration and equipment type transition |  |  |  |  | 2 | 3 | 1 | 5 | 30
49 | Get Ethernet model from MEF |  |  |  |  | 2 | 3 | 1 | 5 | 30
4 | Expand on complex digital payload mappings (modular diagrams) |  |  |  |  | 2 | 2 | 2 | 5 | 40
17 | Improved documentation on POST and DELETE |  |  |  |  | 2 | 2 | 2 | 5 | 40
26 | Description in YANG/UML not good in many places |  |  |  |  | 2 | 2 | 2 | 5 | 40
37 | UNI modelling |  |  |  |  | 2 | 2 | 2 | 5 | 40
6 | More on 3R scenarios |  | #597 |  |  | 2 | 3 | 2 | 5 | 60
20 | RIA improvements (monolith) |  |  |  |  | 2 | 4 | 2 | 5 | 80
34 | All properties conditional |  |  |  | Duplicate of 18 | 2 | 1 | 1 | 99 | 198
35 | Path computation/connectivity computation enhancements |  |  |  | Duplicate of 2 | 2 | 1 | 1 | 99 | 198
51 | Topology discovery… LLDP and TTI |  |  |  | Duplicate of 57/58 | 2 | 1 | 1 | 99 | 198